## Sheet1
Tasks:
start a sale | Iteration 1: |  | iteration 2: |  | iteration 3:
contribute to vice | make important items |  | leave comments |  | add personal collection features
view related products | search functions |  | submit records |  | remove from personal colletion
leave comments | get database started |  | view/post to blogs / FAQ |  | events page
chat with other users | get front end coded |  | start a sale |  | Ebay and craiglist api integration
search by name | establish font end and back end communication |  | chat with other users |  | computers time line
search by manf
submit a computer record
submit a peripheral record | estimation() |  | estimations() |  | estimations()
create personal collection | search | 2 days | leave comments | 2 days | add to personal colletctions | 5 days
make a collection public | database/tables | 3 days | submit records | 1 day | remove from personal colletcion | 2 days
add computer items to collection | Front end code | 5 days | view/post/FAQ | 2 days | events page | 1 days
add peripheral item to collection | establish connetions | 2 days | start sale | 2 days | ebay/craiglist api | 5 days
add software item to collection |  |  | chat with other users | 5 days | computers time line | 3 days
remove an item from personal collection
add a picture to an item in personal collection
view computers in a time line
make a blog post in communit blog
view blog posts
view FAQ
Submit FAQ articles